## Schedule
Axiom Labor Plan Update Schedule: Jan 2023 - Jan 2024 | [11 empty] | Revised: 02/15/23
The calendar is in support of the Rollover and Snapshot processese in the Axiom Labor Plan Files. The Rollover and Snapshot process result in archiving of data related to the approved 'Preliminary Budget' (Rollover) and 'Budget Update' (Snapshot). After each of these processes, the Labor Plan Files are refreshed to support labor planning updates (i.e., updating the "olive section") for the next critical budget development point.
Activity | Responsible | Nov-21 | Dec-21 | Jan-23 | Feb-23 | Mar-23 | Apr-23 | May-23 | Jun-23 | Jul-23 | Aug-23 | Sep-23 | Oct-23 | Nov-23 | Dec-23 | Jan-24
Base budget transfer cutoff deadline | -- | 11/12
FY23 Budget Update is reflected in InformSU | -- |  | 12/1
Financial Managers completed the Axiom labor plan update in the 'Upcoming Budget Year' section to reflect adjustments and/or planning status2 | SCMA Financial Managers |  | 12/10
UBO locks down Axiom labor plan files to complete the rollover process | UBO |  | 12/11 - 12/17 | 1/3
Axiom Labor Plan Files for FY23-24 made available again to users | UBO |  |  | 1/6
UBO schedules working sessions with Financial Managers to go over rollover and snapshot changes made to planfiles, as well as to provide other updates | UBO
Financial Managers perform monthly review and updates in the the Axiom labor plan in the 'Upcoming Budget Year' section (i.e. the olive section), including: a. Address plugs or placeholders in Labor Plan File b. Turnover c. Adjustments to salary as reflected in HR Data d. Planning adjustments as necessary e. Reorgs as necessary f. Other adjs as necessary | SCMA Financial Managers
UBO offers and schedules working sessions with Financial Managers to go over rollover and snapshot changes made to planfiles, as well as to provide other updates | UBO
Preliminary Budget is reflected in InformSU a. Approved Base New Investments for salaries b. Base Reallocations of Salaries (finished by August) c. HR Base Transfers approved in FY23-24 (Promotions and other adjustments effective in FY23 but base transfer was closed) d. Base Faculty Promotions New Investment | -- | [8 empty] | 7/1
HR/Provost Office Base Salary Adjustments: a. Faculty Merit Increases b. Faculty Equity Adjs c. Staff Merit Increases d. Staff Equity Adjs e. SCMA submitted base transfers related to salaries f. Staff promotion adjustments as directed by HR | UBO/HR/Provost Office | [8 empty] | Merit increases for faculty and staff | Base transfers and HR adjustments, including faculty equity, staff equity, and union decisions
All available FY24 Preliminary Budget base salary adjustments are reflected in InformSU and available for reconciliation. | UBO | [9 empty] | 8/1
UBO sends out instructions for 'Reconciling labor planning files to FY24 preliminary budget' | [10 empty] | 8/2
Financial Managers complete their updates to the 'Upcoming Budget Year' of their FY23-24 plan files | SCMA Financial Managers | [9 empty] | 8/31
UBO locks down Axiom labor plan files to complete rollover of the FY23-24 plan files to new FY24-25 plan files | UBO | [9 empty] | 9/1-9/7
Axiom Labor Plan Files for FY24-FY25 made available to users | UBO | [10 empty] | 9/8
Base budget transfer cutoff deadline | Financial Managers | [11 empty] | 10/13
SCMA Financial Managers submit base budget transfers related to the reconciliation of labor plan files | Financial Managers | [11 empty] | 10/13 | through | 12/21
Base adjustments for staff equity and Jesuit staff merit adjustments reflected in InformSU | UBO | [12 empty] | 10/23
UBO begins working with SCMA Financial Managers to implement FY24 Budget Update decisions | UBO/SCMA Financial Managers | [12 empty] | 11/20
FY24 Budget Update is reflected in InformSU | UBO | [13 empty] | 12/1
UBO meets with SCMA FMs to ensure plan file reconciliation | UBO/SCMA Financial Managers | [13 empty] | 12/1-12/21
Financial Managers complete their updates to the 'Upcoming Budget Year' of their FY23-24 plan files to reconcile with the FY24 Budget Update | SCMA Financial Managers | [13 empty] | 12/21
UBO locks down Axiom labor plan files to complete the rollover process | UBO | [13 empty] | 12/22 - 1/5
Axiom Labor Plan Files for FY23-24 made available again to users | UBO | [14 empty] | 1/8